## Budget
BORROWER NAME: |  | TERM: | (#) MONTHS |  | Prepared By: |  |  |  |  | Draw Reqest #:
BUILDER NAME: |  | LOAN: | # |  | Date Prepared: |  |  |  |  | Date Submitted:
PROPERTY ADDRESS: | [9 empty] | Date Funded (Est.):
|  |  |  | NET |  | REVISED
|  | ORIGINAL | EXTERNAL | BUDGET |  | BUDGET | TOTAL |  | REMAINING |  | AMOUNT | % | ADVANCED | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | TOTAL
|  | BUDGET | FUNDING | CCI FUNDING |  | CCI FUNDING | ADVANCED | % | BALANCE | % | OVER | Over | AT CLOSING | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | ADVANCED
| EXPENSE CATEGORY ITEMS | 2007-02-02 | SOURCES | 2007-02-02 | Reallocations | 2007-02-02 | 2007-02-06 | Advanced | 2007-02-06 | Remaining | BUDGET | Budget | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06 | 2007-02-06
01 000 | GENERAL REQUIREMENTS
01 100 | Summary |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 200 | Price and Payment Procedures |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 300 | Administrative Requirements |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 400 | Quality Requirments |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 500 | Temporary Facilities and Control |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 510 | Temporary Utilities |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 520 | Construction Facilities |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 530 | Temporary Construction |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 540 | Construction Aids |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 550 | Vehicular Access and Parking |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 560 | Temporary Barriers and Enclosures |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 570 | Temporary Controls |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 580 | Project Identification |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 600 | Product Requirements |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 700 | Execution Requirements |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 720 | Preparation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 740 | Cleaning |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 800 | Facility Operation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 900 | Facility Decommissioning |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
01 950 | Other General Requirements |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 000 | SITE CONSTRUCTION
02 050 | Basic Site Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 055 | Soil |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 060 | Aggregate |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 065 | Cement and Concrete |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 070 | Geosynthetic |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 080 | Utility Material |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 090 | Joint Material |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 100 | Site Remediation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 110 | Excavation, Removal and Handling of Hazard Material |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 130 | Site Decontamination |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 145 | Groundwater Treatment System |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 200 | Site Preparation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 210 | Subsurface Investigation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 220 | Site Demolition |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 230 | Site Clearing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 300 | Earthwork |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 310 | Grading |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 315 | Excavation and Fill |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 330 | Embankment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 340 | Soil Stabilization |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 370 | Erosion and Sedimentation Control |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 400 | Tunneling, Boring and Jacking |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 500 | Utility Service |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 510 | Water Distribution |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 520 | Well |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 530 | Sanitary Sewerage |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 540 | Septic Tank System |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 550 | Piped Energy Distribution (Hot/Cold Water, Gas, Oil, Steam) |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 580 | Electrical & Communication Structure |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 590 | Site Grounding |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 600 | Drainage and Containment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 660 | Ponds and Reservoir |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 700 | Bases, Ballasts, Pavements and Appurtenance |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 730 | Aggregate Surfacing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 770 | Curbs and Gutter |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 780 | Unit Paver |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 800 | Site Improvements and Amenities |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 810 | Irrigation System |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 815 | Fountain |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 820 | Fences and Gate |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 830 | Retaining Wall |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 850 | Prefabricated Bridge |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 860 | Screening Device |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 870 | Site Furnishing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 880 | Play Field Equipment and Structure |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 890 | Traffic Signs and Signal |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 895 | Markers and Monument |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 900 | Planting/Landscaping |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 950 | Site Restoration and Rehabilitation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
02 975 | Other Site Construction Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 000 | CONCRETE
03 050 | Basic Concrete Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 100 | Concrete Forms and Accessories |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 200 | Concrete Reinforcement |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 300 | Cast-in-Place Concrete |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 400 | Precast Concrete |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 500 | Cementitious Decks and Underlayment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 600 | Grout |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 700 | Mass Concrete |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 900 | Concrete Restoration and Cleaning |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
03 925 | Other Concrete Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 000 | MASONRY
04 050 | Basic Masonry Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 200 | Masonry Unit |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 400 | Stone |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 500 | Refractories |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 600 | Corrosion-Resistant Masonry |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 700 | Simulated Masonry |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 800 | Masonry Assemblies |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 900 | Masonry Restoration and Cleaning |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
04 925 | Other Masonry Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 000 | METALS
05 050 | Basic Metal Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 100 | Structural Metal Framing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 200 | Metal Joist |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 300 | Metal Deck |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 400 | Cold-Formed Metal Framing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 500 | Metal Fabrication |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 510 | Metal Stairs and Ladder |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 520 | Handrails and Railing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 600 | Hydraulic Fabrication |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 700 | Ornamental Metal |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 800 | Expansion Control |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 900 | Metal Restoration and Cleaning |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
05 925 | Other Metal Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 000 | WOOD AND PLASTICS
06 050 | Basic Wood and Plastic Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 100 | Rough Carpentry |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 200 | Finish Carpentry |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 400 | Architectural Woodwork |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 410 | Custom Cabinet |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 415 | Countertop |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 420 | Paneling |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 430 | Wood Stairs and Railing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 470 | Screens, Blinds, Shutter |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 500 | Structural Plastic |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 600 | Plastic Fabrications |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 900 | Wood and Plastic Restoration and Cleaning |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
06 925 | Other Wood and Plastic Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 000 | THERMAL AND MOISTURE PROTECTION
07 050 | Basic Thermal and Moisture Protection Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 100 | Damproofing and Waterproofing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 200 | Thermal Protection |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 210 | Building Insulation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 220 | Roof and Deck Insulation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 240 | Exterior Insulation and Finish Systems (EIFS) |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 300 | Shingles and Roof Tiles |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 400 | Roofing and Siding Panels |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 500 | Membrane Roofing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 590 | Roof Maintenance and Repairs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 600 | Flashing and Sheet Metal |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 700 | Roof Specialties and Accessories |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 800 | Fire and Smoke Protection |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 900 | Joint Sealer |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
07 925 | Other Thermal and Moisture Protection Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 000 | DOORS AND WINDOWS
08 050 | Basic Door and Window Materials and Method |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 100 | Metal Doors and Frame |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 190 | Metal Door Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 200 | Wood and Plastic Door |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 290 | Wood and Plastic Door Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 300 | Specialty Door |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 400 | Entrances and Storefront |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 500 | Window |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 590 | Window Restoration and Replacement |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 600 | Skylight |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 700 | Hardware |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 790 | Hardware Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 800 | Glazing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 890 | Glazing Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 900 | Glazed Curtain Wall |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 990 | Glazed Curtain Wall Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
08 995 | Other Door and Window Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 000 | FINISHES
09 050 | Basic Finish Materials and Method |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 100 | Metal Support Assemblies |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 110 | Non-Load-Bearing Wall Framing |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 120 | Ceiling Suspension |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 130 | Accoustical Suspension |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 190 | Metal Frame Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 200 | Plaster and Gypsum Board |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 280 | Plaster Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 300 | Tile |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 390 | Tile Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 400 | Terrazzo |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 490 | Terrazzo Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 500 | Ceiling |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 590 | Ceiling Assembly Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 600 | Flooring |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 610 | Floor Treatment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 620 | Specialtiy Flooring |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 630 | Masonry Flooring |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 640 | Wood Flooring |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 680 | Carpet |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 690 | Flooring Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 700 | Wall Finishes |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 790 | Wall Finish Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 800 | Acoustical Treatment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 900 | Paints and Coatings |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 910 | Paint |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 930 | Stains and Transparent Finishes |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 940 | Decorative Finishes |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 960 | High-Performance Coating |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 990 | Paint Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
09 995 | Other Finishes |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 000 | SPECIALTIES
10 100 | Visual Display Boards |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 150 | Carpartments and Cubicles |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 200 | Louvers and Vents |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 240 | Grilles and Screens |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 300 | Fireplaces and Stoves |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 330 | Fireplace and Stove Restoration |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 350 | Flagpoles |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 400 | Identification Devices |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 430 | Exterior Signage |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 440 | Interior Signage |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 500 | Locker |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 520 | Fire Protection Specialties |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 530 | Protective Covers |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 550 | Postal Specialties |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 600 | Partitions |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 670 | Storage Shelving |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 700 | Exterior Protection |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 800 | Toilet, Bath and Laundry Accessories |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 900 | Wardrobe and Closet Specialties |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
10 950 | Other Specialty Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0%
11 000 | EQUIPMENT
11 010 | Maintenance/Cleaning Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 020 | Security and Vault Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 160 | Loading Dock Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 170 | Solid Waste Handling Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 250 | Water Softening Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 260 | Disinfectant Feed Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 280 | Hydraulic Gates and Valve |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 680 | Office Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
11 990 | Other Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 000 | FURNISHINGS
12 100 | Art |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 300 | Manufactured Casework |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 400 | Furnishings and Accessiories |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 500 | Furniture |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 600 | Multiple Seating |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 700 | Systems Furniture |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 800 | Interior Plants and Planter |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 900 | Furnishings Restoration and Repair |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
12 950 | Other Furnishings |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 000 | SPECIAL CONSTRUCTION
13 020 | Building Module |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 030 | Special Purpose Room |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 150 | Swimming Pool |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 170 | Tubs and Pools |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 400 | Measurement and Control Instrumentation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 500 | Recording Instrumentation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 600 | Solar and Wind Energy Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 700 | Security Access and Surveillance |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 800 | Building Automation and Control |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 850 | Detection and Alarm |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 900 | Fire Suppression |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
13 950 | Other Special Construction Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 000 | CONVEYING SYSTEMS
14 100 | Dumbwaiter |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 200 | Elevator |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 300 | Escalators and Moving Walk |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 400 | Lift |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 500 | Material Handling |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 600 | Hoists and Crane |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 700 | Turntable |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 800 | Scaffolding |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 900 | Transportation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
14 950 | Other Conveying Systems |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 000 | MECHANICAL |  |  |  |  | 0
15 050 | Basic Mechanical Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 080 | Mechanical Insulation |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 100 | Building Services Piping |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 200 | Process Piping |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 300 | Fire Protection Piping |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 400 | Plumbing Fixtures and Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 410 | Plumbing Fixtures |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 440 | Plumbing Pump |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 460 | Water Conditioning Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 480 | Water Heater |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 490 | Pool and Fountain Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 500 | Heat-Generation Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 510 | Heating Boilers and Accessories |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 530 | Furnace |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 540 | Fuel-Fired Heater |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 550 | Breechings, Chimneys and Stack |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 600 | Refrigeration Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 610 | Refrigeration Compressor |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 670 | Refrigerant Condensing Unit |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 700 | Heating, Ventilating, and Air Conditioning Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 710 | Heat Exchanger |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 720 | Air Handling Unit |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 730 | Unitary Air Conditioning Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 740 | Heat Pump |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 750 | Humidity Control Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 760 | Terminal Heating and Cooling Unit |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 770 | Floor-Heating and Snow Melting Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 800 | Air Distribution |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 810 | Ducts |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 830 | Fans |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 850 | Air Outlets and Inlet |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 860 | Air Cleaning Devices |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 900 | HVAC Instrumentation and Controls |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
15 950 | Other Meechanical Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 000 | ELECTRICAL
16 050 | Basic Electrical Materials and Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 100 | Wiring Methods |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 120 | Conductors and Cable |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 130 | Raceway and Boxes |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 140 | Wiring Devices |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 150 | Wiring Connection |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 200 | Electrical Power |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 300 | Transmission and Distribution |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 400 | Low-Voltage Distribution |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 500 | Lighting |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 510 | Interior Luminaries |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 520 | Exterior Luminaries |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 550 | Special Purpose Lighting |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 700 | Communications |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 720 | Telephone and Intercommunication Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 770 | Cable Transmission and Reception Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 780 | Broadcast Transmission and Reception Equipment |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 800 | Sound and Video |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
16 900 | Other Electrical Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
50 000 | TENANT IMPROVEMENTS
50 100 | Tenant Improvements |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
50 200 | Other Tenant Improvements |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
51 000 | (FUTURE CLASSIFICATION)
51 100 | (Future Expense Category) |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
52 000 | DEVELOPER PROFIT AND OVERHEAD
52 100 | Developer Profit and Overhead |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
53 000 | CONTRACTOR PROFIT AND OVERHEAD
53 100 | Contractor Profit and Overhead |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
| SUBTOTAL DEVELOPER/BUILDER COSTS | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0%
54 000 | GENERAL PROJECT/CONSTRUCTION COSTS
54 025 | Marketing, Advertising, Promotions |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 050 | Administrative (Salarieis, Office, Etc.) |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 075 | Project Management |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 100 | Leasing Commissions |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 125 | Common Area Maintenance - Prior to HOA |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 150 | Permits and Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 175 | Zoning Verification Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 200 | Survey Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 225 | Geotechnical Soil Report Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 250 | Environmental Report Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 275 | Appraisal Report Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 300 | Architecture Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 325 | Engineering Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 350 | Inspection Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 375 | Brokerage Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 400 | Legal Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 425 | Insurance Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 450 | Utilities |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 475 | R.E. Taxes |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 500 | Accounting/Audit |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 525 | Courier/Printing/Parking Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 550 | Bond Premium/LC Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
54 575 | Other Construction Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
TOTAL HARD AND SOFT CONSTRUCTION COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 000 | CONTINGENCY ALLOWANCE |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
TOTAL CONSTRUCTION COSTS PRIOR TO ACQUISTION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 000 | ACQUISITION
56 100 | Project Acqusition/Refinance |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
56 200 | Title and Recording Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
56 300 | Other Acquistion & Closing Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
TOTAL CONSTRUCTION COSTS / NET LOAN AMOUNT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 000 | FINANCING COSTS | [23 empty] | 0
57 100 | Interest CCI |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
57 200 | Interest 3rd Party Passthrough Lender |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
57 300 | Interest Partner |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
57 400 | Interest Seller |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
57 500 | CCI Partner Fee |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
57 600 | Origination Fees |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
57 700 | Other Financing Costs |  |  | 0 |  | 0 | 0 | 0% | 0 | 0% | 0 | 0% | [12 empty] | 0
| Total Financing Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL ALL COSTS / PRINCIPAL LOAN AMOUNT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRINCIPAL LOAN BALANCE OUTSTANDING | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTEREST AMORTIZATION CALCULATION
Loan Balance Outstanding for interest calc | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
less: Capital Partnering Fees and 3rd Party Interest | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NLA for interest calculation | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest Amortization: |  | 9.32% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Less: Prepaid Interest at Closing | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Interest Amortization | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I/we hereby confirm the the trueness and correctness of this Budet and all Updates as of the dated stated herein:
Signatures:
|  | Borrower: |  |  |  | Date:
I/we hereby authorize and approve this draw and do approve all prior disbursements on this loan to date:
Signatures:
(Required Before Disbursement)
|  | Borrower |  |  |  | Date:
(Required Before Disbursement)
|  | CCI Accountant: |  |  |  | Date:
(Required Before Disbursement)
|  | CCI V.P. of Construction Management |  |  |  | Date:
(Required Before Disbursement)
|  | CCI V.P. of Lending |  |  |  | Date:
(Required Before Disbursement)
|  | CCI President/CEO |  |  |  | Date:
Formulas:
BUDGET = SUM([TERM:])
BUDGET = SUM([BUDGET])
TOTAL = SUM([TOTAL])
TOTAL = +[DRAW]
REMAINING = SUM([TOTAL])
DRAW = SUM([ADVANCED])
DRAW = SUM([DRAW])